## Roadmap Overview
RICHERWEALTH — PHASE-WISE REACT DEVELOPMENT ROADMAP
Full-stack AI-powered wealth management platform — from login to news, built with free-tier APIs wherever possible
Phase | Phase Name | Duration | Priority | Key Features / Modules | Frontend / Backend Additions | Free APIs & Tools | Status
0 | Planning, Architecture & UX Design | 2 wks | MVP | Requirements freeze; user personas; information architecture; wireframes for Dashboard, Portfolio, AI Chat; DB schema design (assets, liabilities, transactions, users); API contract (GraphQL/REST) design | Figma wireframes; monorepo setup (Turborepo/Nx); Next.js 15 + TS scaffold; ESLint/Prettier; CI/CD skeleton (GitHub Actions) | Figma (free), Excalidraw (free), dbdiagram.io (free), GitHub Actions (free tier) | Not Started
1 | Foundation — Auth, DB & Core Infra | 3 wks | MVP | Signup/login (email+password, OTP, social), MFA, passkeys, session mgmt, RBAC, onboarding flow, user profile & settings, multi-currency base setup | Next.js 15 + React 19 + TS; NestJS API; PostgreSQL + Prisma; Redis for sessions; Zustand for client state; React Hook Form + Zod | Supabase Auth (free tier) or Auth.js/NextAuth (free, self-hosted); Twilio free trial OTP or Firebase Auth (free) for OTP/social login; WebAuthn (passkeys, free/open standard) | Not Started
2 | Dashboard Shell & Net Worth Engine | 3 wks | MVP | Home dashboard: Total Net Worth, Today's Gain/Loss, Monthly/Annual Growth, Asset Allocation donut, Net Worth trend chart, glassmorphism animated cards, empty states | Recharts + Apache ECharts for charts; Framer Motion for animated cards; TanStack Query for data fetching; WebSocket gateway (NestJS) for live net-worth ticking | None external yet — computed from internal DB; Recharts/ECharts (free/open-source) | Not Started
3 | Manual Asset & Liability Entry (All Classes) | 3 wks | MVP | CRUD for every asset type from the spec: cash, bank/FD/CDs, retirement (401k/NPS/EPF/PPF), insurance, vehicles, collectibles, NFTs, business equity, real estate (manual valuation), loans/liabilities | Dynamic form builder (React Hook Form + Zod schemas per asset type); AG Grid for tabular asset lists; file upload for supporting docs (S3-compatible storage) | Cloudflare R2 free tier or Supabase Storage (free tier) for document/receipt uploads | Not Started
4 | Stocks & Global Market Data Integration | 3 wks | Core | Live holdings tracking, live price, P/E, EPS, CAGR, dividend, intrinsic/fair value estimate, watchlists, NSE/BSE/NYSE/NASDAQ/LSE/HKEX support | Price-sync worker (NestJS cron/BullMQ + Redis queue); server-side caching layer; WebSocket price ticks to client | Alpha Vantage (free: 25 req/day); Finnhub (free tier, US/global); Twelve Data (free 800 req/day); yahoo-finance2 npm (free, unofficial) as fallback; NSE India via jugaad-data / nsepython (free, unofficial) for Indian equities | Not Started
5 | Mutual Funds, ETFs & Bonds | 2 wks | Core | SIP & lumpsum tracking, XIRR/CAGR/NAV calc, expense ratio, portfolio overlap, rolling returns, bond holdings (govt/corp/muni/SGB) | XIRR calculation service (Newton-Raphson in Node); scheduled NAV sync job | MFAPI.in (100% free, no key, India MF NAV history); Alpha Vantage/Finnhub for global ETFs; AMFI India NAV bulk file (free, official, daily) | Not Started
6 | Crypto Integration | 1.5 wks | Core | Multi-exchange wallet tracking, live prices for BTC/ETH/SOL/alts, portfolio P&L, price alerts | Polling/WebSocket service for crypto prices; wallet-address read-only tracking (optional) | CoinGecko API (free, generous limits, no key for basic use); CoinCap API (free) as fallback | Not Started
7 | Commodities, Forex & Precious Metals | 1.5 wks | Core | Gold (physical/digital/ETF/jewellery), silver, oil/gas/wheat/coffee/corn/copper, forex holdings, multi-currency conversion everywhere in the app | Currency normalization service (base-currency conversion for net worth roll-up) | GoldAPI.io (free tier) or metals-api.com (free tier, limited calls) for gold/silver; Frankfurter.app (free, ECB, no key) or exchangerate.host (free) for forex; Alpha Vantage commodities endpoint (free tier) for oil/wheat/etc. | Not Started
8 | Real Estate & Alternative Assets | 2 wks | Core | Residential/commercial/agricultural/rental properties, land/plots, purchase price vs current estimate, appreciation, rental yield, loan-linked ROI; startup investments, PE, REITs, P2P lending, collectibles | Property card UI with photo gallery + map pin; manual appreciation-assumption engine (until valuation API is added) | OpenStreetMap + Leaflet (free, open-source) for property maps instead of paid Mapbox; Mapbox free tier (50k loads/mo) as upgrade option | Not Started
9 | Liabilities & Loan Intelligence | 2 wks | Core | Education/car/personal loans, mortgages, credit cards; EMI schedule, interest breakdown, remaining balance, prepayment-savings suggestion engine | Amortization-schedule calculator service (shared with Calculators module) | None external — pure calculation engine | Not Started
10 | Income, Expenses & Banking Sync | 3 wks | Core | Income sources (salary/business/rental/dividends/royalties/freelance), auto-categorized expenses, bank/UPI/card auto-sync, cash-flow view | Transaction-categorization ML/rules service; bank aggregator webhook consumer | Plaid Sandbox (free for dev, US/EU banks); Salt Edge free dev tier (EU); for India: Setu Account Aggregator or manual CSV/statement import as free fallback (India open banking APIs are largely paid) | Not Started
11 | Portfolio Analytics Engine | 3 wks | Core | Allocation, diversification score, sector/geography/currency exposure, Beta, Alpha, Sharpe/Sortino/Treynor ratios, std deviation, max drawdown, correlation matrix, Monte Carlo simulation | Python microservice (FastAPI) for quant calculations (numpy/pandas/scipy) called via internal REST from NestJS; Apache ECharts heatmaps for correlation matrix | Historical price data reused from Phase 4-7 API integrations; risk-free rate from FRED API (free, US Treasury data) | Not Started
12 | Risk Engine | 2 wks | Core | Portfolio health, liquidity risk, debt risk, inflation risk, currency risk, market/interest-rate/credit risk scoring feeding into Wealth Health Score | Rules + weighted-scoring engine (Node service) consuming Analytics Engine outputs | FRED API (free) for inflation/interest-rate macro data | Not Started
13 | Goals & Calculators | 2 wks | Core | Goal planner (House/Marriage/Vacation/Education/Retirement/Car/Custom) with AI success-probability; SIP/EMI/Mortgage/Retirement/Inflation/Lumpsum/Compound Interest/SWP/FD/RD/Loan-Comparison/Tax/Currency calculators | Reusable financial-math library (shared client+server via shared TS package) | None external — pure calculation; currency calc reuses Phase 7 forex API | Not Started
14 | Market Intelligence & News | 2 wks | Core | Live world markets, indices, currencies, crypto, commodities, top gainers/losers, breaking news feed, economic & IPO calendar, Fed/RBI rates, inflation, GDP | News aggregation cron job with dedup + sentiment tagging; economic-calendar widget | NewsAPI.org (free dev tier, 100 req/day) or GNews.io (free tier) for breaking news; Finnhub news endpoint (free tier); FRED API (free) for Fed/GDP/inflation; RBI open data (free, India rates); Trading Economics free/limited calendar as optional add-on | Not Started
15 | Tax Center | 2 wks | Core | Short/long-term capital gains, dividend tax, tax-loss harvesting suggestions, country-specific tax reports, downloadable reports | Country-specific tax-rule config (JSON-driven, extensible); PDF report generator | None external — rule-based; country tax slabs maintained as internal config data | Not Started
16 | Encrypted Document Vault | 2 wks | Core | Store PAN/Aadhaar/Passport/insurance/property docs/statements/tax returns with client-side (zero-knowledge) encryption | AES-256 client-side encryption before upload; key management via user-derived key | Supabase Storage / Cloudflare R2 (free tier) as encrypted-blob storage backend | Not Started
17 | Alert & Notification Center | 1.5 wks | Core | Market crash, dividend, loan/premium/EMI/SIP due, stock target hit, property price alert, crypto alert; in-app + push + email | Rules engine + BullMQ scheduled jobs; notification-preferences center | Firebase Cloud Messaging (free) for push; Resend or SendGrid free tier for email | Not Started
18 | Reports Engine | 2 wks | Core | PDF/Excel/CSV export, professional & institutional-grade report templates, AI-written executive summaries | Server-side PDF generation (Puppeteer/React-PDF); Excel export via ExcelJS/openpyxl microservice | None external — internal templating; Puppeteer/ExcelJS are free/open-source | Not Started
19 | AI Analyst & AI Chat (Core AI Layer) | 4 wks | Core | Daily/weekly/monthly/yearly AI reports, natural-language AI Chat ('Should I buy Apple?', 'Can I retire at 50?'), Sell/Buy/Rebalance/Tax-harvest suggestions | RAG pipeline over user's financial data (pgvector or Pinecone free tier); LLM orchestration service; streaming chat UI | Claude API or OpenAI API (pay-as-you-go, has free trial credits) for reasoning; open-source local LLM via Ollama (Llama 3/Mistral, fully free, privacy-sensitive analysis) as a cost-free fallback; pgvector (free, Postgres extension) for RAG instead of paid vector DB | Not Started
20 | Advanced AI Features | 4 wks | Advanced | Wealth Digital Twin, AI CFO proactive alerts, Future Wealth Simulator (crash/inflation/salary scenarios), Opportunity Scanner, Wealth Health Score (0-100), Financial Time Machine, Wealth Timeline, Wealth DNA classifier, One-Click Financial Audit (30-50 page report), AI Copilot | Simulation engine (Monte Carlo + scenario trees, reused from Phase 11); background AI Copilot worker; scoring model combining Phases 11+12 outputs | Same LLM stack as Phase 19; historical macro data from FRED (free) for simulations | Not Started
21 | Family Office Mode & Estate Planning | 2 wks | Advanced | Track parents/spouse/children/joint accounts/family trust/shared properties, inheritance planning, nominees, will/trust/beneficiaries, asset-transfer workflows | Multi-profile linking with granular RBAC/sharing permissions | None external — internal data model extension | Not Started
22 | Security Hardening, Testing & QA | 2 wks | MVP | Penetration-test pass, OWASP checklist, audit logging, role-based access review, unit/integration/E2E test suites, load testing | Jest + React Testing Library + Playwright E2E; k6 for load testing; Snyk/OWASP ZAP scans | OWASP ZAP (free, open-source); Snyk free tier; k6 (free, open-source); GitHub Actions (free tier) for CI test gates | Not Started
23 | Performance, Polish & UX Pass | 2 wks | MVP | Lighthouse/Core Web Vitals optimization, skeleton loaders, dark mode, mobile responsiveness, accessibility (WCAG AA), micro-interactions polish | Code-splitting/lazy-loading audit; Framer Motion polish pass; axe-core accessibility audit | axe DevTools (free), Lighthouse CI (free, open-source) | Not Started
24 | Deployment, Monitoring & Launch | 1 wk | MVP | Production deploy, CDN, monitoring/alerting, error tracking, beta launch, feedback loop | Vercel/Render deployment; Sentry error tracking; Grafana/Prometheus or hosted dashboards | Vercel (free hobby tier) or Render (free tier) for hosting; Sentry (free tier, 5k errors/mo); Better Uptime / UptimeRobot (free tier) for monitoring | Not Started
Legend:
MVP | Must ship for first usable release
Core | Full-featured product, phase 2 rollout
Advanced | Differentiator / competitive-moat features
Total estimated timeline: ~54 weeks (~13 months) for a small team (2-4 engineers). Update the Status column as work progresses.

## Free APIs Reference
FREE / FREE-TIER APIs — QUICK REFERENCE
Category | API / Service | Free Tier Limit | Auth Needed? | Used In Phase(s) | Notes / Link
Auth / Identity | Supabase Auth | 50k MAU free | N/A (you configure) | 1 | supabase.com — email/social/OTP/passkeys included
Auth / Identity | Auth.js (NextAuth) | Fully free, self-hosted | N/A | 1 | authjs.dev — open source, unlimited
Auth / Identity | Firebase Auth | 10k verifications/mo free (phone OTP) | API key | 1 | firebase.google.com/products/auth
Stocks - Global | Alpha Vantage | 25 requests/day (free key) | API key (free) | 4, 11 | alphavantage.co — global equities, fundamentals, forex, commodities
Stocks - Global | Finnhub | 60 calls/min free tier | API key (free) | 4, 14 | finnhub.io — real-time quotes + news
Stocks - Global | Twelve Data | 800 requests/day free | API key (free) | 4 | twelvedata.com — stocks, forex, crypto
Stocks - Global | yahoo-finance2 (npm) | Unofficial, generous, no key | None | 4 | Community-maintained wrapper around Yahoo Finance endpoints — use as fallback, can break
Stocks - India | jugaad-data / nsepython | Free, unofficial NSE scraper | None | 4 | Python libs for NSE/BSE India live & historical data
Mutual Funds - India | MFAPI.in | 100% free, no key, no limit stated | None | 5 | mfapi.in — daily NAV for all India AMFI mutual funds
Mutual Funds - India | AMFI NAV bulk file | Free, official, daily download | None | 5 | amfiindia.com — authoritative NAV source
Crypto | CoinGecko API | 10-30 calls/min free (no key for public endpoints) | Optional API key for higher limits | 6 | coingecko.com/en/api — 13,000+ coins
Crypto | CoinCap API | Free, no key | None | 6 | coincap.io — good fallback for CoinGecko
Forex | Frankfurter.app | Free, no key, ECB-sourced | None | 7, 13 | frankfurter.app — daily reference rates
Forex | exchangerate.host | Free tier | Optional key | 7, 13 | exchangerate.host
Commodities / Metals | GoldAPI.io | Free tier (100 req/mo) | API key (free) | 7 | goldapi.io — live gold/silver spot prices
Commodities / Metals | metals-api.com | Free tier (50 req/mo) | API key (free) | 7 | metals-api.com — precious metals + base metals
Commodities - Broad | Alpha Vantage Commodities | Shares 25 req/day limit | API key (free) | 7 | Oil, wheat, coffee, corn, copper endpoints
Macro / Economic Data | FRED API | Free, unlimited (fair use) | API key (free) | 11, 12, 14, 20 | fred.stlouisfed.org — US Fed rates, inflation, GDP, Treasury yields
Macro / Economic Data | RBI Open Data | Free, official | None | 14 | India central bank rates & data
News | NewsAPI.org | 100 requests/day (dev tier) | API key (free) | 14 | newsapi.org — breaking news aggregation
News | GNews.io | 100 requests/day free | API key (free) | 14 | gnews.io — alternative news aggregator
Company Fundamentals | Financial Modeling Prep | 250 requests/day free | API key (free) | 4, 11 | financialmodelingprep.com — fundamentals, ratios, statements
Banking / Open Banking | Plaid Sandbox | Free for development/testing | API key (free, sandbox) | 10 | plaid.com — US/EU bank account linking (production tier is paid)
Banking / Open Banking | Salt Edge | Free dev tier | API key (free, dev) | 10 | saltedge.com — EU-focused; India equivalents are largely paid (Setu AA)
Maps | OpenStreetMap + Leaflet | Fully free, open-source | None | 8 | leafletjs.com — property location maps, no billing risk
Maps | Mapbox | 50,000 free map loads/month | API key (free) | 8 | mapbox.com — richer styling, upgrade path
Storage / Documents | Supabase Storage | 1GB free tier | API key (free) | 3, 16 | Encrypted document vault backend
Storage / Documents | Cloudflare R2 | 10GB free storage/mo | API key (free) | 3, 16 | S3-compatible, no egress fees
Notifications | Firebase Cloud Messaging | Free, unlimited push | API key (free) | 17 | Push notifications, iOS/Android/Web
Notifications | Resend | 3,000 emails/month free | API key (free) | 17 | resend.com — transactional email
AI / LLM | Ollama + Llama 3 / Mistral | Fully free, self-hosted, local | None | 19, 20 | ollama.com — zero-cost AI layer for privacy-sensitive analysis
AI / LLM | Claude API / OpenAI API | Free trial credits, then pay-per-use | API key | 19, 20 | Best reasoning quality; budget for production use beyond free credits
AI / Vector Search | pgvector (Postgres ext.) | Free, open-source | None | 19 | RAG storage — avoids paid vector DB (Pinecone free tier also viable)
Hosting | Vercel (Hobby) | Free tier for frontend/Next.js | N/A | 24 | vercel.com — generous free tier for early stage
Hosting | Render | Free tier for backend services | N/A | 24 | render.com — good NestJS/Postgres free tier
Monitoring | Sentry | 5,000 errors/month free | API key (free) | 24 | sentry.io — error tracking
Monitoring | UptimeRobot | 50 monitors free | API key (free) | 24 | uptimerobot.com — uptime alerts
Note: Free tiers change over time and rate limits are low — cache aggressively (Redis) and add a paid-tier upgrade path (e.g., Alpha Vantage Premium, Polygon.io) before scaling past beta.

## Tech Stack
TECHNOLOGY STACK SUMMARY
Layer | Technology | Purpose
Frontend | React 19 + Next.js 15 (App Router) + TypeScript | Core UI framework, SSR/streaming, type safety
Frontend | Tailwind CSS + shadcn/ui | Styling system and accessible component primitives
Frontend | Framer Motion | Animated cards, glassmorphism effects, micro-interactions
Frontend | Recharts + Apache ECharts | Portfolio charts, heatmaps, correlation matrices
Frontend | TanStack Query | Server-state caching, live data sync
Frontend | Zustand | Lightweight global client state
Frontend | React Hook Form + Zod | Form handling & schema validation
Frontend | AG Grid | Large tabular data (holdings, transactions)
Frontend | Leaflet / Mapbox GL | Real-estate location visualization
Backend | Node.js + NestJS | Modular API server, dependency-injected services
Backend | PostgreSQL + Prisma ORM | Primary relational database & type-safe queries
Backend | Redis | Caching, session store, BullMQ job queues
Backend | GraphQL + REST | API contracts — GraphQL for flexible dashboard queries, REST for integrations/webhooks
Backend | WebSockets (Socket.IO / native) | Live price ticks, real-time net worth updates
Backend | FastAPI (Python microservice) | Quant analytics — Sharpe/Sortino/Monte Carlo via numpy/pandas/scipy
AI Layer | Claude API / OpenAI API | Financial explanations, AI Chat, report generation
AI Layer | Ollama (local LLM) | Privacy-sensitive analysis at zero marginal cost
AI Layer | pgvector (RAG) | Retrieval-augmented generation over user documents/transactions
Data & Integrations | See 'Free APIs Reference' sheet | Market data, news, banking, crypto, forex, commodities
Security | OAuth 2.0 + Passkeys (WebAuthn) | Modern passwordless-capable authentication
Security | AES-256 client-side encryption | Zero-knowledge document vault
Security | RBAC + audit logs | Family Office / multi-user permission control
DevOps | Vercel (frontend) + Render/Fly.io (backend) | Hosting on free/low-cost tiers
DevOps | GitHub Actions | CI/CD pipelines, automated testing gates
DevOps | Sentry + UptimeRobot | Error tracking & uptime monitoring
Testing | Jest + React Testing Library + Playwright | Unit, integration, and E2E testing